## Summary
UK Restock Plan — Summary
Extracted from the Supply Chain Tracker. All figures are calculated live from the sheets in this workbook.
Key Alerts
UK Warehouse Shipping: No open purchase orders are currently shipping to the UK warehouse.
UK Stockout Risk: 9 of 9 SKUs are at High stockout risk in the UK warehouse; 9 of those currently have zero replenishment in transit to UK.
Purchase Order Risk: 2 of 6 open PO(s) are flagged High Risk and require follow-up.
Retail Partner Demand: No opening stocking order quantities from the 3 new UK retail partners have been entered yet (UK Restock Plan column K) — restock quantities below currently reflect DTC demand only and are likely understated.
UK Launch Readiness
UK Launch Date | 2026-09-21
Weeks Until Launch | 5.8571
Retail Partner Stocking Qty Entered (Units) | 0
Total UK Restock Units Needed | 4600
SKUs On Track (Sea Freight) | 0
SKUs Needing Expedited Air | 9
SKUs Critical — May Miss Launch | 0
Open POs Needing Follow-Up | 3
Notes & Assumptions
• This is a standalone extract of the UK Restock Plan and PO Follow-Ups from the Supply Chain Tracker workbook, with the supporting Purchase Orders, Inventory & Coverage, and Reference Data carried along so every formula still resolves independently of that file.
• See the UK Restock Plan tab to edit the Launch Date / Target Weeks of Cover assumptions — this Summary and every dependent formula recalculates from there.
• Get the initial stocking order quantities from the 3 new UK retail partners and enter them per SKU in UK Restock Plan column K as soon as they're known — until then, every recommended order quantity on this sheet reflects DTC demand only.

## UK Restock Plan
UK Restock Plan
Launch Assumptions (editable):
UK Launch Date | 2026-09-21 | 3 new UK retail partners launch in 6 weeks (from 2026-08-10) — edit if the date shifts
Target Weeks of Cover at Launch | 10 | EDIT ME — desired DTC buffer of stock at launch (retail partner stocking is separate, see column K below)
New UK Retail Partners Launching | 3 | Informational — their per-SKU opening stocking orders go in column K (Retail Partner Launch Stocking Qty) once known
Today's Date (reference) | 2026-08-11
Weeks Until Launch | 5.8571
SKU | Product | Factory | Factory City | UK On-Hand Qty | Weekly Sell- Through Rate (DTC only) | Open PO Qty to UK | Current UK Weeks of Cover | Current UK Stockout Risk | Projected UK On-Hand at Launch | Retail Partner Launch Stocking Qty (Units) | Target Qty at Launch | Order Qty Needed (Pre-MOQ) | Factory MOQ (Units) | Recommended Order Qty | Production Lead Time (Wks) | Sea Transit to UK (Wks) | Air Transit to UK (Wks) | Total Lead Time — Sea | Total Lead Time — Air | Recommended Ship Method | Order-By Date | Launch Readiness
HN-RB-300 | Recovery Balm 300ml | Factory A | Shenzhen | 35 | 75 | 0 | 0.46667 | High Risk | 0 | 0 | 750 | 750 | 500 | 750 | 3 | 5 | 1 | 8 | 4 | Air — Expedite | 2026-08-24 | Expedite Required
HN-FS-050 | Face Serum 50ml | Factory A | Shenzhen | 20 | 45 | 0 | 0.44444 | High Risk | 0 | 0 | 450 | 450 | 500 | 500 | 3 | 5 | 1 | 8 | 4 | Air — Expedite | 2026-08-24 | Expedite Required
HN-BW-200 | Body Wash 200ml | Factory B | Chiang Mai | 50 | 55 | 0 | 0.90909 | High Risk | 0 | 0 | 550 | 550 | 400 | 550 | 2.5 | 4.5 | 1 | 7 | 3.5 | Air — Expedite | 2026-08-27 12:00 | Expedite Required
HN-HM-100 | Hair Mask 100ml | Factory C | Jakarta | 25 | 30 | 0 | 0.83333 | High Risk | 0 | 0 | 300 | 300 | 300 | 300 | 3 | 5 | 1 | 8 | 4 | Air — Expedite | 2026-08-24 | Expedite Required
HN-LB-250 | Lip Balm 3-Pack | Factory D | Taipei | 40 | 60 | 0 | 0.66667 | High Risk | 0 | 0 | 600 | 600 | 1000 | 1000 | 2 | 5 | 0.85714 | 7 | 2.8571 | Air — Expedite | 2026-09-01 | Expedite Required
HN-SM-150 | Scalp Mist 150ml | Factory C | Jakarta | 10 | 20 | 0 | 0.5 | High Risk | 0 | 0 | 200 | 200 | 300 | 300 | 3 | 5 | 1 | 8 | 4 | Air — Expedite | 2026-08-24 | Expedite Required
HN-EO-030 | Essential Oil Blend 30ml | Factory E | Chiang Mai | 8 | 15 | 0 | 0.53333 | High Risk | 0 | 0 | 150 | 150 | 200 | 200 | 2 | 4.5 | 1 | 6.5 | 3 | Air — Expedite | 2026-08-31 | Expedite Required
HN-BC-400 | Bath Crystals 400g | Factory F | Ho Chi Minh City | 15 | 25 | 0 | 0.6 | High Risk | 0 | 0 | 250 | 250 | 500 | 500 | 4 | 5 | 1 | 9 | 5 | Air — Expedite | 2026-08-17 | Expedite Required
HN-NC-075 | Night Cream 75ml | Factory A | Shenzhen | 18 | 40 | 0 | 0.45 | High Risk | 0 | 0 | 400 | 400 | 500 | 500 | 3 | 5 | 1 | 8 | 4 | Air — Expedite | 2026-08-24 | Expedite Required
TOTAL | [9 empty] | 0 |  |  |  | 4600
Notes & Assumptions
• SKU, Product, Factory, and current UK inventory/coverage figures are linked live from Inventory & Coverage — this sheet has no re-entered source data.
• IMPORTANT GAP: Weekly Sell-Through Rate (column F) is the DTC-only rate from the source data. It does not include demand from the 3 new UK retail partners. Column K (Retail Partner Launch Stocking Qty) is where their opening stocking orders should be entered per SKU once known — it currently defaults to 0, so Target Qty at Launch and every recommendation to its right currently reflect DTC demand ONLY and likely understate what's actually needed for launch.
• Projected UK On-Hand at Launch assumes steady depletion at the current (DTC-only) Weekly Sell-Through Rate between today and the Launch Date, plus any PO quantity already open to UK (column G) landing before launch. It does not assume the newly recommended order below arrives in time — that is what the lead-time/readiness columns to the right test.
• Recommended Order Qty rounds the pre-MOQ need up to the factory's MOQ (a partial-MOQ need still requires ordering a full MOQ batch).
• Recommended Ship Method / Launch Readiness compare each lead-time option (Production Lead Time + Sea or Air transit to UK) against Weeks Until Launch: Sea if it fits, Air if only Air fits, otherwise flagged Critical even with Air.
• Order-By Date = Launch Date minus the recommended method's total lead time. If this date is already in the past, that order is overdue and should be placed immediately.
• Change the Launch Date, Target Weeks of Cover, or any Retail Partner Launch Stocking Qty and every recommendation on this sheet recalculates.
Formulas:
Order-By Date = IF([Recommended Order Qty]=0,"N/A",B4-IF([Recommended Ship Method]="Sea",[Total Lead Time — Sea],[Total Lead Time — Air])*7)

## PO Follow-Ups
PO Follow-Ups
All fields link live from Purchase Orders / Inventory & Coverage — no PO data is re-entered here.
PO # | Factory | SKU | Product | Qty | Status | PO Risk Flag | Destination Warehouse | Affects UK Restock? | Follow-Up Needed? | Recommended Action | Priority
PO-410 | Factory A | HN-RB-300 | Recovery Balm 300ml | 500 | In production — on track | Low Risk | HK | Yes — UK Critical SKU | No | No follow-up needed — monitor for on-time delivery. | Low
PO-411 | Factory A | HN-NC-075 | Night Cream 75ml | 500 | In production — on track | Low Risk | US | Yes — UK Critical SKU | No | No follow-up needed — monitor for on-time delivery. | Low
PO-412 | Factory C | HN-HM-100 | Hair Mask 100ml | 300 | Production delayed — raw material shortage | High Risk | Unknown | Yes — UK Critical SKU | Yes | Contact factory for a revised production timeline. If this is a UK-critical SKU, evaluate air freight or a backup factory to recover schedule. | Urgent — UK Launch Impact
PO-413 | Factory D | HN-LB-250 | Lip Balm 3-Pack | 1000 | Completed — ready for pickup | Medium Risk | Unknown | Yes — UK Critical SKU | Yes | Issue shipping instructions now. Goods are finished and awaiting dispatch — assign a destination and carrier immediately to avoid storage delays. | Urgent — UK Launch Impact
PO-414 | Factory E | HN-EO-030 | Essential Oil Blend 30ml | 200 | Unconfirmed — awaiting factory response (4 days) | High Risk | Unknown | Yes — UK Critical SKU | Yes | Escalate to factory immediately — no confirmation received. Confirm the production slot or reallocate the PO to a backup factory. | Urgent — UK Launch Impact
PO-415 | Factory F | HN-BC-400 | Bath Crystals 400g | 500 | In production — on track | Low Risk | US | Yes — UK Critical SKU | No | No follow-up needed — monitor for on-time delivery. | Low
Notes & Assumptions
• Every PO is listed (not just flagged ones) so the sheet reflects the full open-PO picture; use the Follow-Up Needed and Priority columns to triage.
• Affects UK Restock? flags Yes when the PO's SKU currently shows High UK stockout risk on Inventory & Coverage — i.e. this factory's output matters for the UK launch even though the PO itself may not ship to UK.
• Priority is 'Urgent — UK Launch Impact' when a non-Low-Risk PO involves a UK-critical SKU, since resolving it protects the UK launch specifically.
• Recommended Action is derived from keywords in the Status text and recalculates automatically if a PO's status is updated.

## Purchase Orders
Purchase Orders
Blue text = source input data entered from PO records. Black text = formulas (do not overwrite).
PO # | Factory | Factory City | SKU | Product | Qty | Status | Destination Warehouse | Ship Method | Stated ETA Notes | Stated ETA (Weeks) | Ref. Sea Transit (Wks) | Ref. Air Transit (Wks) | Applicable Ref. Transit (Wks) | PO Risk Flag | Ships to UK Warehouse?
PO-410 | Factory A | Shenzhen | HN-RB-300 | Recovery Balm 300ml | 500 | In production — on track | HK | Sea | Ships to HK, ETA 3.5 weeks | 3.5 | 0.28571 | 0.14286 | 0.28571 | Low Risk | No
PO-411 | Factory A | Shenzhen | HN-NC-075 | Night Cream 75ml | 500 | In production — on track | US | Sea | Ships to LA, ETA 4 weeks | 4 | 3 | 0.71429 | 3 | Low Risk | No
PO-412 | Factory C | Jakarta | HN-HM-100 | Hair Mask 100ml | 300 | Production delayed — raw material shortage | Unknown | Unknown | Originally ETA 3 weeks, now unknown | Unknown | N/A | N/A | N/A | High Risk | No
PO-413 | Factory D | Taipei | HN-LB-250 | Lip Balm 3-Pack | 1000 | Completed — ready for pickup | Unknown | Unknown | Awaiting shipping instructions | Unknown | N/A | N/A | N/A | Medium Risk | No
PO-414 | Factory E | Chiang Mai | HN-EO-030 | Essential Oil Blend 30ml | 200 | Unconfirmed — awaiting factory response (4 days) | Unknown | Unknown | Unknown | Unknown | N/A | N/A | N/A | High Risk | No
PO-415 | Factory F | Ho Chi Minh City | HN-BC-400 | Bath Crystals 400g | 500 | In production — on track | US | Sea | Ships to LA, ETA 6 weeks (sea) | 6 | 3.5 | 0.71429 | 3.5 | Low Risk | No
TOTAL |  |  |  |  | 3000
Notes & Assumptions
• Destination Warehouse and Ship Method are extracted from each PO's status/ETA notes as provided; recorded as 'Unknown' where the source did not specify a destination or method yet.
• Ship Method is assumed 'Sea' where not explicitly stated but the ETA is multi-week in scale (consistent with sea freight lead times in Reference Data); PO-415 explicitly stated '(sea)'.
• PO Risk Flag is a formula that searches the Status text for keywords ("delayed", "Unconfirmed", "Completed", "on track") — edit the Status text and the flag recalculates automatically.
• Reference Sea/Air Transit columns are pulled live from the Reference Data Shipping Lead Times table via the Factory City + Destination Warehouse route — they show the typical transit time for that lane, for comparison against the Stated ETA.

## Inventory & Coverage
Inventory & Coverage
Stockout Risk Thresholds (editable assumptions):
High Risk if Weeks of Cover < | 4
Medium Risk if Weeks of Cover < | 8 | (Low Risk otherwise)
SKU | Product | Category | Primary Factory | US (LA) Qty | UK (Manchester) Qty | HK Qty | Total Qty | Weekly Sell- Through Rate | Total Weeks of Cover | Total Stockout Risk | UK Weeks of Cover | UK Stockout Risk | Open PO Qty (All Dest.) | Open PO Qty to UK
HN-RB-300 | Recovery Balm 300ml | Body Care | Factory A | 220 | 35 | 110 | 365 | 75 | 4.8667 | Medium Risk | 0.46667 | High Risk | 500 | 0
HN-FS-050 | Face Serum 50ml | Skincare | Factory A | 150 | 20 | 75 | 245 | 45 | 5.4444 | Medium Risk | 0.44444 | High Risk | 0 | 0
HN-BW-200 | Body Wash 200ml | Body Care | Factory B | 180 | 50 | 60 | 290 | 55 | 5.2727 | Medium Risk | 0.90909 | High Risk | 0 | 0
HN-HM-100 | Hair Mask 100ml | Hair Care | Factory C | 90 | 25 | 45 | 160 | 30 | 5.3333 | Medium Risk | 0.83333 | High Risk | 300 | 0
HN-LB-250 | Lip Balm 3-Pack | Skincare | Factory D | 300 | 40 | 80 | 420 | 60 | 7 | Medium Risk | 0.66667 | High Risk | 1000 | 0
HN-SM-150 | Scalp Mist 150ml | Hair Care | Factory C | 70 | 10 | 30 | 110 | 20 | 5.5 | Medium Risk | 0.5 | High Risk | 0 | 0
HN-EO-030 | Essential Oil Blend 30ml | Wellness | Factory E | 45 | 8 | 20 | 73 | 15 | 4.8667 | Medium Risk | 0.53333 | High Risk | 200 | 0
HN-BC-400 | Bath Crystals 400g | Body Care | Factory F | 60 | 15 | 25 | 100 | 25 | 4 | Medium Risk | 0.6 | High Risk | 500 | 0
HN-NC-075 | Night Cream 75ml | Skincare | Factory A | 130 | 18 | 55 | 203 | 40 | 5.075 | Medium Risk | 0.45 | High Risk | 500 | 0
TOTAL |  |  |  | 1245 | 221 | 500 | 1966 | [5 empty] | 3000 | 0
Notes & Assumptions
• Product, Category, and Primary Factory are looked up live from the Reference Data Product Catalog — SKU is the only identifying input needed on this sheet.
• Weekly Sell-Through Rate is a single blended rate per SKU (not broken out by warehouse), as provided in source data. UK Weeks of Cover therefore approximates the UK warehouse independently covering total demand at that SKU's overall sell-through rate — read it as a directional risk indicator, not a precise per-location forecast.
• Open PO Qty columns pull live from the Purchase Orders sheet (SUMIF/SUMIFS by SKU), so incoming replenishment updates automatically as POs change.
• Risk thresholds in B4:B5 are editable assumptions — changing them recalculates every Stockout Risk flag on this sheet.

## Reference Data
Reference Data
Fulfillment Warehouses
Warehouse Code | Region / Name | City
US | US West | Los Angeles
UK | UK | Manchester
HK | Asia | Hong Kong
Product Catalog
SKU | Product | Category | Primary Factory
HN-RB-300 | Recovery Balm 300ml | Body Care | Factory A
HN-FS-050 | Face Serum 50ml | Skincare | Factory A
HN-BW-200 | Body Wash 200ml | Body Care | Factory B
HN-HM-100 | Hair Mask 100ml | Hair Care | Factory C
HN-LB-250 | Lip Balm 3-Pack | Skincare | Factory D
HN-SM-150 | Scalp Mist 150ml | Hair Care | Factory C
HN-EO-030 | Essential Oil Blend 30ml | Wellness | Factory E
HN-BC-400 | Bath Crystals 400g | Body Care | Factory F
HN-NC-075 | Night Cream 75ml | Skincare | Factory A
Factory Network
Factory | City | Country | SKUs Produced | MOQ | MOQ (Units, Numeric) | Production Lead Time (Weeks) | Status
Factory A | Shenzhen | China | HN-RB-300, HN-FS-050, HN-NC-075 | 500 units/SKU | 500 | 3 | Active — reliable, primary partner
Factory B | Chiang Mai | Thailand | HN-BW-200 | 400 units | 400 | 2.5 | Active — reliable
Factory C | Jakarta | Indonesia | HN-HM-100, HN-SM-150 | 300 units/SKU | 300 | 3 | Active — occasional delays
Factory D | Taipei | Taiwan | HN-LB-250 | 1,000 units | 1000 | 2 | Active — high MOQ but fast
Factory E | Chiang Mai | Thailand | HN-EO-030 | 200 units | 200 | 2 | New — first PO in progress
Factory F | Ho Chi Minh City | Vietnam | HN-BC-400 | 500 units | 500 | 4 | Active — long lead time
Shipping Lead Times
Origin (Factory City) | Destination (Warehouse Code) | Sea Freight (Weeks) | Air Freight (Days) | Air Freight (Weeks) | Route Key
Shenzhen | US | 3 | 5 | 0.71429 | Shenzhen¦US
Shenzhen | UK | 5 | 7 | 1 | Shenzhen¦UK
Shenzhen | HK | 0.28571 | 1 | 0.14286 | Shenzhen¦HK
Chiang Mai | US | 4.5 | 6 | 0.85714 | Chiang Mai¦US
Chiang Mai | UK | 4.5 | 7 | 1 | Chiang Mai¦UK
Chiang Mai | HK | 4 | 2 | 0.28571 | Chiang Mai¦HK
Jakarta | US | 4 | 6 | 0.85714 | Jakarta¦US
Jakarta | UK | 5 | 7 | 1 | Jakarta¦UK
Jakarta | HK | 4 | 2 | 0.28571 | Jakarta¦HK
Taipei | US | 3 | 4 | 0.57143 | Taipei¦US
Taipei | UK | 5 | 6 | 0.85714 | Taipei¦UK
Taipei | HK | 0.28571 | 1 | 0.14286 | Taipei¦HK
Ho Chi Minh City | US | 3.5 | 5 | 0.71429 | Ho Chi Minh City¦US
Ho Chi Minh City | UK | 5 | 7 | 1 | Ho Chi Minh City¦UK
Ho Chi Minh City | HK | 3 | 1 | 0.14286 | Ho Chi Minh City¦HK
Notes & Assumptions
• Blue text = source input data. Black text = formulas that recalculate automatically.
• Air Freight is converted from days to weeks (÷ 7) in column E for comparison with Sea Freight.
• Shenzhen→HK and Taipei→HK Sea Freight were stated in the source as '2 days' (an outlier vs. all other Sea Freight entries, which were given in weeks); converted to weeks (2/7 ≈ 0.29) here for unit consistency with the rest of the column.
• Route Key (column F) concatenates Origin City + Destination Warehouse Code and is used by Purchase Orders and UK Restock Plan lookups.
• MOQ and Production Lead Time figures are as provided by the factory network source data. MOQ (Units, Numeric) parses the stated MOQ into a plain number for use in restock-quantity formulas.